## TODO LIST
Change Tasks row color | New Main Features | New Small Features | Repeated Weekly
Change API Path x version | Daily Reward | Target List Ordinabile | Skins
Test Registration email | Achivements | Task counter in upgrade | Profile Pics
Attack delay | Badges | Crew Invitation | Achievements
Crew Chat | Researches | Task duration in upgrade | Badges
Fix Scan timers bug | Crew Wars | Google Play integration | Statistics
Create 50 random(10) players | Advanced Hacking | Upgrade Advisor
BETA1.0.0 | Customizable Malwares | Shield
Botnet Malware | Staff (to buff the stats) | Local Notification for tasks
RAT Malware |  | RAT Redesign/Improvement
Bug BETA1.0.1 |  | Sounds
BETA1.0.1 |  | Research Notification
Global Chat |  | Notification Center
Missions |  | Overclock Improvement
Crew Delete |  | Honeypot ??
Crew Change Description |  | Tournament Attack/Defense
Crew give ownership |  | Miner (ASIC) - 10+level/h, manually start the miner
Crew Wallet |  | Sell unused items for 25% value
Bug BETA1.0.1
BETA1.0.2 |  | Next:
New Hosting Website |  | RAT Sort Options
Password Reset |  | Preview Upgrades with Researches
Failed Attempts |  | Collect All Missions
Global Search in Console |  | Block temp mail
Token Renew |  | Mission Sort Options
Tutorial |  | IP Reputation
BETA1.0.3 |  | Achievement Sort
Official Beta |  | Tutorial updated
New Home UI |  | Bugfixes
BETA1.0.16
New Terminal
Beta 1.0.20
Offers
Items
Beta
Crew Shop
Tournaments
Messages
Player Settings
Skill Tree
IAP
Bug Fixes
Official Release

## Bugs
BugID | Bug Name | Bug Description | Status | Severity | Notes
7 | Money not refreshed in Home | Money in Home Scene are not updated | FIXED | Medium | Need to removeScene
6 | Double actions while lagging | On slower devices/internet connections, some actions are repeated (Crew Chat&Upgrades) | Testing | Medium | Add a switch between tapping and receiving response
5 | Software Keyboard UI | On devices with software keyboards the UI should be adjusted | Testing | High | actualContentHeight or androidSystemUiVisibility
4 | Player Stats - static ip | Everyone see 127.0.0.1 as his own IP, it is not :D | FIXED | Info | Easy to fix
3 | Console - Manual IP floating text box | if you go to console, then to Crew (when not in a Crew) and then back to console, the textbox will be in an wrong position | FIXED | Medium | Check textfield, try to reposition in scene view
2 | Negative Score | Negative Reputation check doesn't work | FIXED | Low
1 | Activation Token Invalid | Activation Code must be URLEncoded for + sign | FIXED | Critical